## Burndown Chart
Burndown Chart for JavaScript Automation Testing and Analysis Project
Hours planned per week
Task No | Major Project Tasks | Total Expected Hours | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
T1 | Initial Discussion about Research Topic with IS | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2 | Project Proposal Initial Draft Creation and Submission | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3 | Initial level risk and quality analysis | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4 | Project Proposal Final Draft Submission/Document Verification | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5 | Self Study of JavaScript Regular Expression | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T6 | Creating Practice Practical Test for SE101 and Testing in Jasmine | 10 | 0 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
T7 | Modify the Practice Practical Test using Regular Expression and Testing | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
T8 | Discussion and finalising the Methodology essay topic and did basic research | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
T9 | Google research to Identify popular testing frameworks and other online surveys | 5 | 0 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0
T10 | Preparing questions for Survey and submitting for review | 8 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
T11 | Attended meetups (IITP, Tech Cluster, JavaScript and SQL) | 10 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0
T12 | Create Paper and Electronic Survey | 8 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0
T13 | Ethical Approval form collection and document preparation | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
T14 | Submission and Getting Ethical Approval | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
T15 | Conducted Survey | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0
T16 | Self study of Testing Frameworks | 10 | 0 | 2 | 2 | 2 | 0 | 1 | 0 | 1 | 2 | 2
T17 | Survey Result Analysis | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 0
T18 | Setup of testframework cucumber from H drive | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0
T19 | Implement Classic example in Jasmine | 8 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 2 | 0 | 0
T20 | Start setup other frameworks (Mocha-Chai assert/expect/should) | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3
T21 | Triangle exercise in Mocha-Chai Assert/Expect/Should and Cucumber | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
T22 | Study of Selenium IDE and Selenium WebDriver | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
T23 | Online Survey Ethical Application and Approval | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
Expected Work Hours |  | 150 | 18 | 20 | 13 | 17 | 16 | 10 | 7 | 20 | 18 | 11
Actual Work Hours |  | 147 | 18 | 20 | 13 | 17 | 16 | 12 | 5 | 17 | 18 | 11
Notes
Week 6 - T14 Expected Hours was 2, But delayed in getting Ethical Approval and took extra 2 hrs
Week 7- T18 Expected Hrs was 5, But finished within 3 Hrs, saved 2 hrs
Week 8 -T19 Expected Hrs was 8, But finished in 5Hrs, saved 3 hrs
Week 10-T21 Expected Hrs was 5 , But finished in 3Hrs, saved 2 hrs
Week 10-T22 Expected Hrs was 3 , But finished in 5Hrs,took extra 2hrs
(147 Actual Hrs + 3hrs saved) = 150 Expected Hrs